## Blad1
Datum | Planned? | Julia | Shené
2026-02-02 | Field research
2026-02-04 | Functional design, Initializing github space, Database op zetten | Function design [Eat in/to-go scherm, Betaal scherm, Review order scherm], Database | Function design [Start scherm, Menu scherm, Item Bestellen scherm]
2026-02-06 | Design afmaken(?), planning opzetten, begin maken aan frontend | Planning, design afmaken(?), begin maken aan frontend startpagina
2026-02-09 |  | Frontend startpagina afmaken, frontend cart/order overview beginnen | Design afmaken(?), Frontend menu beginnen
2026-02-11 |  | Frontend cart/order overview afmaken, API Design beginnen | Frontend menu afmaken, Frontend menu specifiek item beginnen
2026-02-13 |  | Werken aan API Design/Afmaken(?), Adding items beginnen, Removing items starten | Frontend menu specifiek item afmaken, Frontend Payment screen beginnen
2026-02-23 |  | API moet af zijn, Adding items afmaken, Removing items afmaken, Adding items with + & - icons starten | Frontend payment screen afmaken, placing and order beginnen
2026-02-25 |  | API, testing/bugfixing | Placing an order afmaken, Receipt printing beginnen (If possible, otherwise testing/bugfixing)
2026-02-27 |  | testing/bugfixing | testing/bugfixing
2026-03-02 |  | testing/bugfixing | testing/bugfixing
2026-03-04 |  | testing/bugfixing | testing/bugfixing
2026-03-06 |  | testing/bugfixing | testing/bugfixing